## Project_Schedule
| Phase of Development | Activities to be carried out | Deadline | Deadline
1 | Analysis and Specification | In this phase,the existing problem, the requirement of project for solution, the tools and platforms to be used for the implementation of the project were analyzed.
2 | Designing | In this phase various bots which were to be used for the extraction of data and to perform other tasks were designed.
3 | Implementation | In this phase, the bots were integrated with a website where all the necessary data would be displayed to the user.
4 | Testing | In this phase the website was tested for various parameters to ensure its core funtionality and the desired output.

## Record of Activities(Monthwise)
Month | 2020-07-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | Studied various project ideads, the final year project idea decided was RPA based faculty assistant.
Week2 | The idea was reviewed by Project Review committee and many improvements were made to the project.
Week3 | Various possible methods were analyzed for the implementation of the project.
Week4 | The idea is again presented to Project Review Committee where they suggested more features and some more ways to implement.
Month | 2020-08-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | The Project was finally assigned by Project Review committee and the title was “ Faculty Assistant Using RPA”.
Week2 | Research work was started about existing systems and their flaws and how those could be rectified with this project.
Week3 | Experimented with different automation tools like UiPath, Blue Prism to select which could be the most suitable for the project.
Week4 | Selecting UiPath,enrolled in the UiPath course offered by UiPath Academy
Month | 2021-09-20
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | Made regular updates on the social media pages to achieve some traction from potential audience.
Week2 | Researched about possible structure and content for the website and framework to be used.
Week3 | Designed a bot to extract the list of schools, colleges and universities from the websites of CBSE and AICTE which is to be used for website.
Week4 | Studied how useful data can be extracted from the web using UiPath
Month | 2021-10-20
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | Started creating the website by making a homepage and login page.
Week2 | Created a dashboard for the website where the info about tasks allocation and its state will be displayed.
Week3 | Created the schema of database of website for the data to be imported and displayed on dashboard of the website.
Week4 | Used Bootstrap to modify dashboard and table to make it more presentable to user.
Month | 2021-11-20
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | Created an admin page for admin to add new users for the website.
Week2 | Using UiPath created a bot to read information from excel sheet.
Week3 | Updated the bot to check the students who have "N" against their courses and print names.
Week4 | Again updated the bot to mail the students who have "N" against their courses.
Month | 2021-12-20
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | Further upgradation of bot to check for the same in google sheets using google API.
Week2 | Creating another bot for checking of synopsis and ppt from different drives.
Week3 | Integrating both the bots with website.
Week4 | Creating and integrating a database that is connected to both the UiPath bot and the website such that the changes from the bot can be reflected to our website.
Month | 2021-02-21
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | Improving our webiste and including charts to relay the information about students who have completed the course and who have not.
Week2 | Using UiPath orchestrator to schedude the bots according to the user.
Week3 | Added a default excel sheet format to show user which type of format is acceptable for the bots to work.
Week4 | Added a feature to send a list of students to user who haven't completed the course with the respective dates they were supposed to do it.
Month | 2021-03-21
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | Researched on various chatbots and how to train them.
Week2 | Creation of another RPA bot that would send the username and password to the new user account created by admin.
Week3 | Integrating the latest bot that would send the email to new users created by the admin.
Week4 | Integration of the trained chatbot with our website.